INVITATION TO BID FOR CONSULTANCY

| 1 | Title of Consultancy | ADVERTISEMENT: TERMS OF REFERENCE FOR THE DEVELOPMENT OF ADAPTED SHORT-TERM JOB ORIENTED CURRICULLUM FOR AGRI-BUSINESS IN SOMALIA |  |
| --- | --- | --- | --- |
| 2 | SCI Contracting Office | Save the Children Somalia/land Country Office |  |
| 3 | Period of Consultancy | The duration of this assignment overall is 45 days, including preparation of the curriculum and resources as well as training of instructors. Specific schedules will be agreed upon with the selected individual consultant/consultancy firm. |  |
| 4 | Consultant type required | Consultancy Firm/Individual |  |
| 5 | Responsibility for Logistics arrangements and Costs | Save the children will pay the consultant fee in a lump sum and will not reimburse any incurred costs during the assignment. The consultant will cover their own Logistical arrangements, costs; including food, accommodation, local transport and all cost associated with data collection work and whole activities. |  |
| 6 | Taxation Provisions | The consultancy firm/Consultant shall be responsible for all taxes arising from the consultancy in line with the local Tax regulations applicable at the SCI contracting office. |  |
| 7 | Travel requirements | The consultancy firm/Individual Consultant will cover all travel costs (tickets) and arrange local travel to field sites. |  |
| 8 | Security requirements | The consultancy firm/individual Consultant will comply with standard of Save the Children Security procedures, including the completion of SCI online security training (applicable to international consultants) prior to travel to Somalia. |  |
| 9 | Professional quality and Expertise | The following are the minimum requirements for the Consultant Firm/individual to be considered for carrying out the assignment. - Advanced University degree in education, agriculture, learning psychology or Pedagogy, economics, environment or related field - At least 7 years’ experience in market-oriented curriculum development and training, especially in agri-business or related field - Experience in client-centered training development and facilitation including the use of participatory tools for information harvesting. - Demonstrated experience and proven record in employment or workforce development using market systems approach - demonstrated ability to produce clear, compelling, and succinct analytical report wide variety of stakeholders including the private sector that inform quality curriculum development. - Excellent communication and documentation skills. - Strong background and experience in using participatory design process during curriculum development process to align to client needs. - Demonstrable experience in conducting research prior to curriculum |  |
| 10 | EVALUATION CRITERIA The proposals submitted by consulting companies will be evaluated based on the following criteria: |  |  |
|  | Essential Criteria |  | Pass/Fail |
| 1 | The Bidder and its staff must agree and Sign to comply with SCI policies embedded below at this ITB. The Bidder is to download below listed items, read, understand and sign off appropriate section in below. a) Terms & Conditions of Bidding b) Supplier Sustainability Policy and the included mandatory policies |  | Pass/Fail |
| 2 | A valid Certificate of Registration from the relevant Ministry of Commerce from Ministry Of commerce of Federal Republic of Somalia – NB: This is only applicable to firms and not individual consultants For |  | Pass/Fail |
| 4 | A valid Tax Compliance Certificate the relevant ministry of Finance/Revenue Authority of Federal Republic of Somalia – NB: This is only applicable to firms and not individual consultants |  | Pass/Fail |
|  | Capability Criteria (Technical Evaluation): |  |  |
| 5 | Detailed technical proposal with clear understanding of the TOR and Methodology of how the consultant intends to conduct assignment with detailed work plan, clear milestones, methodologies, data analyses plan including any software to be used for analysis. This to be evaluated based on: - Overall quality, clarity, organization and relevance of the technical proposal document - The level of work plan detail and how it is related to the proposed methodology 30 marks |  |  |
| 6 | Two Copies of the previous similar reports relevant to the subject matter. |  |  |
| 7 | Submit official and genuine signed bank statement from 1st May 2025 to 30th April 2026. |  |  |
| 8 | Experience in conducting similar assignments related to the subject matter as proven experience. This to be evaluated based on: - Prior experience in design for job-oriented curriculum for agri-business- Please provide at least two contracts and/or LPOs - Two CVs for the proposed technical team detailing qualifications and experience. 2 CVs are only applicable for the consultancy firm - Please clarify. One CV is enough for individual consultant. - Cover letter introducing the company/individual, outlining their technical expertise and interest for the assignment including their technical suitability. - Updated Company Profile (Optional) |  |  |
|  | Commercial Criteria (Financial Evaluation): |  |  |
| 9 | Detailed financial proposal with budget breakdown including all expenses, fees, and taxes. 100% x Lowest bid valueCurrent value bid x X% |  |  |
| Note: For the technical analysis, a company must pass the essential criteria and score 60% and above on the capability to be considered in the next evaluation process and the ultimate decision will be based on interview performance |  |  |  |
| 11 | Application Procedure | - Interested consultant (s) who meet the consultancy requirements are requested to submit their bid and each application package should include the above required minimum requirements. Applications can be submitted by: Protected Email box below - Email should be addressed to Somalia.Tenders@savethechildren.org - Should you need any clarifications please direct your queries to Somalia.procurement@savethechildren.org and expect responses within maximum of two working days. - Note – this is a sealed tender box which will not be opened until the tender has closed. Therefore, do not send tender related questions to this email address as they will not be answered. The subject of the email should be TERMS OF REFERENCE FOR THE DEVELOPMENT OF ADAPTED SHORT-TERM JOB ORIENTED CURRICULLUM FOR AGRI-BUSINESS IN SOMALIA - All attached documents should be clearly labelled so it is clear to understand what each file relates to. - Emails should not exceed 15mb – if the file sizes are large, please split the submission into two emails. - Do not copy other SCI email addresses into the email when you submit it as this will invalidate your bid. All applications MUST be submitted on or before the closing date below to be considered for the assignment. Only shortlisted Candidates will be contacted. |  |
| 12 | Closing date for Applications | Interested consultants shall submit their applications through the above procedures or before 19th May 2026, EAT at 11:59 PM. |  |

| We, the Bidder, hereby confirm we compliance with the following policies and requirements: |  |  |
| --- | --- | --- |
| Policy | Policy / Document | Signature |
| Terms & Conditions of Bidding |  |  |
| Supplier Sustainability Policy and the included mandatory policies | Click Here to Access |  |

| We confirm that Save the Children may in its consideration of our offer, and subsequently, rely on the statements made herein. |  |
| --- | --- |
| Signature: | ………………………………………………….. |
| Name: | ………………………………………………….. |
| Title: | ………………………………………………….. |
| Company: | ………………………………………………….. |
| Date: | ………………………………………………….. |

TERMS OF REFERENCE FOR THE   DEVELOPMENT OF ADAPTED SHORT-TERM JOB ORIENTED CURRICULLUM FOR AGRI-BUSINESS IN SOMALIA.

# Action Title: Initiative for Marketable Practices in Agri-business, Circular Economy and Technology (IMPACT).

# Project SOF: 20801179.

# Dates: 01 January 2025 - 31 December 2027.

Project Locations: Somalia.

Thematic Areas: Child Poverty - Food Security and Livelihoods – TVET.

# Sub themes: TVET.

# Project Objective: To increase access to renewable energy, accelerate transition to the circular economy, and expand sustainable agri-food value chains in Somalia.

1.    INTRODUCTION

Save the Children is the world’s leading independent organization for children. We work in 120 countries. We save children’s lives; we fight for their rights; we help them fulfil their potential.

We work together, with our partners, to inspire breakthroughs in the way the world treats children and to achieve immediate and lasting change in their lives. Following a major transition, our international programmes are now delivered through a merged operation with 15,000 staff, managed through seven regional hubs and reporting to a relatively small, central office. We’re changing to become more efficient, more aligned, a better partner, a stronger advocate, a magnet for world-class people and relevant for the 21st century.

Save the Children has worked in Somalia since 1951 when we set up a vocational school for orphaned boys in Somalia. From the early 1970s we have provided emergency assistance when the needs demand. Each year, about 650,000 people benefit from our longer-term development work in Health, Nutrition, Water, Sanitation & Hygiene (WASH), Education, Food Security and Livelihoods (FSL), Child Protection and Child Rights Governance.

Youth unemployment remains one of the biggest challenges towards peace and stabilization in project target districts and regions. Somalia has one of the largest proportional youth populations in the world. It is estimated that 73 percent of the Somali population is aged under 30. Within this group, internally displaced youth and young returning refugees are considered among the most marginalized and at-risk groups in the country.

TVET presents an opportunity to engage the country’s youth, yet enrollment in both TVET and tertiary education remains at just 5% of the eligible population. The TVET system is significantly underdeveloped, underfunded, and has limited coordination, with major disparities in access between urban and rural areas.

Furthermore, there is a significant gender gap in TVET and employment participation.  Constraints that affect women include early and forced marriage, gender-based violence, early pregnancies which lead women to regress their access to higher technical education. Pervasive social norms, that entrench from early childhood, which discourage women from participating in male dominated sector including Energy, trade and agribusiness further inhibit their active participation in high growth sectors. Inequitable hiring practices for women and People with Disabilities (PwD) also present immense constraints in accessing decent jobs from employers.

Regarding systemic constraints in TVET, the limited standardized qualifications for TVET instructors and limited institutional management degrade training quality and lead to graduates with limited alignment to market demands who could have tapped significantly to project target location for green growth sector.

- PROJECT BACKGROUND

The IMPACT project therefore addresses these constraints by creating pathways for skill development in emerging green sectors (renewable energy, circular economy and agri-business). The project ensures that Somali youth and adults have the necessary competencies to engage in sustainable livelihoods. The initiative is aligned with Somalia National Development Plan (NDP-9) and Somalia NDP3, which emphasizes the importance of renewable energy, climate resilience, and inclusive economic development. It also contributes to achieving Sustainable Development Goals (SDGs) 4 (Quality Education), 5 (Gender Equality) 7 (Affordable and Clean Energy), 8 (Decent Work and Economic Growth), and 13 (Climate Action).

The Initiative for Marketable Practices in Agri-business, Circular Economy and Technology (IMPACT) is implemented by Save the Children in collaboration with consortium partners ADRA, Windle International, and Shaqodoon. The project aims to boost green skills in project target locations, focusing on renewable energy, the circular economy, and sustainable agribusiness. The initiative seeks to enhance Technical and Vocational Education and Training (TVET) centres, strengthen public-private coordination, and build a skilled workforce to promote green growth, equitable jobs, and climate resilience. The Project is implemented in Somalia and works with key government agencies including MoES and MoLSAF.

IMPACT is set to achieve its ambitions in Somalia and Somalia through 3 interconnected objectives:

- Output 1: Somali female and male youth obtain marketable climate resilient green skills in renewable energy, circular economy, and sustainable agribusinesses

- Output 2: Enhanced institutional capacity of TVET centres and professional technical secondary schools in Somalia to effectively deliver training in marketable green skills in renewable energy, circular economy, and sustainable agribusiness

- Output 3: Strengthened capacity of public institutions to effectively manage, monitor, and coordinate green skills initiatives in renewable energy, circular economy, and sustainable agribusiness.

The project uses client centered and market systems approaches to created sustained changes at systems level.  The aim is to enhance private sector involvement in supporting women, IDPs, PwDs, and other vulnerable groups in creating sustainable livelihoods. IMPACT identifies green growth companies in renewable energy, circular economy, and agri-business value chains, analyse value creation in these sectors, and demonstrate approaches to create linkage between TVETs and green companies for skilling and employment creation.

- OVERALL OBJECTIVE OF THE ASSIGNMENT

Save the Children is looking for a qualified consulting firm or individual consultant with substantive and cutting-edge background in employment creation, Technical Vocational Education and Training (TVET) with specialized experience and skills in market-oriented curriculum development in agri-business curriculum development in key sub-trades namely greenhouse farming, integrated pest management, drip-irrigation and agro-processing.  These were pre-identified high growth sub sectors identified in a labour market assessment finding. A strong background in curriculum development is key especially using participatory design process tools to ensure the curriculum aligns with the needs and priorities of the clients including the private sector. Therefore, the aim of the curriculum is to guide and support vocational training centres on how to deliver these pre-identified agri-business occupations. It will enable TVETs to create a structured learning programme that offers training for youth in these occupations thus making the curricula competency-based, hence making it practical and work-base focused. Key structure of the curricula will be a syllabus, trainer guide, learner guide with comprehensive curricula content for each of the module.

There have been existing curricula developed in the agri-business sector including agriculture curriculum for the technical secondary education by GIZ. Other organizations including UNDP, SCI has also developed curricula in these trades and therefore, the consultant will develop an adapted-market oriented curricula from these existing resources.

3. SPECIFIC OBJECTIVES OF THE ASSIGNMENT

The purpose of this consultancy is to develop market-oriented agri-business curriculum focusing on sub-trades (greenhouse farming, integrated pest management, drip-irrigation and agro-processing) which will be trained on and adopted by Target public and private sector training institutions.There have been existing curricula developed in the agri-business sector including agriculture curriculum for the technical secondary education by GIZ. Other organizations including UNDP, SCI has also developed curricula in these trades and therefore, the consultant will develop an adapted-market oriented curricula from these existing resources.  Therefore, the assignment will be primarily desk-based with few KIIs/FGDs to be collated from participating private entities, youth and TVET directorates to streamline market needs with supply needs.

The curricula should be exclusively based on the priorities of target clients, market systems including companies and the future of work in Somalia. The curricula should contain syllabus, trainer guide and trainee manual with all resources including teaching aid materials presented through interactive designs (etc. visuals). The consultant should develop the curricula by undertaking a through desk review of existing curricula in the agri-business sector combined with KIIs and FGDs from youth, partners, communities and the TVET directorate and develop a customized, fit-for-purpose curriculum that aligns with needs and priorities of the market. These mixed method approaches will enable triangulated evidence and identify entry points for developing the curricula. Below are more step-by-step objectives of curricula development.

- Regional diagnosis. Review what training resources in the selected agri-business sub-sectors (greenhouse farming, integrated pest management, drip-irrigation and agro-processing) that exist within the Somalia TVET ecosystem to develop a fit-for-purpose curriculum. The consultant is expected to perform a thorough analysis of the relevance of content, pedagogical landscape, relevance to market demands in Somalia, and materials that will be adapted to develop a custom-made, job-oriented curriculum.

- Combine interviews with women/youth learners to understand their aspirations and draw their initial perspectives and thoughts towards a potential agri-business curriculum. these user thoughts will provide substantive inputs and insights to the development of a client-oriented curriculum.

- Conduct consultative meetings/ interviews of both KIIs and FGDs with existing TVET providers, project teams, TVET directorates, companies providing agri-business apprenticeships, and other relevant bodies/institutions to harvest information to obtain inputs on lessons learned, gaps, and potential content/inputs for the curricula

- Collaborate with MoES and MoLSA/F during the curriculum development process, ensuring that the developed curriculum is aligned with the national training priorities and national Qualification frameworks for the TVET sector in Somalia.

- Present the revised curricula to the relevant authorities including the TVET directorate and do the required changes and adjustments to ensure it fits the overall strategic framework of TVET and also fits with some of the strategic initiatives including GIZ secondary modular TVET. Share the final reviewed curricula with Save the Children for final review and approval.

- The final products must contain training materials, complete Syllabus with training tools including a trainer’s guide, trainee manual, and other necessary materials/tools to Save the Children team.

- Identify existing capacity gaps from existing capacity assessment reports pertaining to the agri-business training provision potential and develop a TOT training package for target instructors to enable delivery of market-oriented agri-business skills. Ensure training approach is streamlining with the content and pedagogical requirements of the developed curriculum. Training should be participatory and client oriented.

4. SCOPE OF WORK

The curricula will be implemented in pre-identified target locations in Somalia. The curriculum development will focus on a number of stakeholders including MoES and MolSAF, EU, IMPACT consortium partners, TVET centers, youth learners, agri-business companies and communities in target locations.

5. Content of the Curriculum for agribusiness curriculum:

- Greenhouse Farming.

- Drip Irrigation /Advanced irrigation systems.

- Agro-processing.

- Integrated Pest Management (IPM).

- Pest detection systems.

- Land preparation techniques: Soil health management (e.g., conservation tillage, cover crops).

- Climate-resilient crops, fisheries and livestock practices.

- Climate smart and environmentally friendly farming techniques.

- Post-harvest management and value addition.

6. Methodology

The overall curriculum development will heavily entail a desk review and adapting existing curricula pertaining to the agri-business sector. This will be combined a qualitative interview to integrate aspirations and perspectives into the curriculum. Qualitative assessment will include FGDs/KIIs from youth, community representatives, agri-business firms, project partners and TVET directorate.  The steps mentioned below form a more detailed approach of the curriculum development process.

- Review existing desk information including existing agri-business curriculum from key organizations including GIZ, UNDP and Save the Children. Further review about existing government owned TVET frameworks as well as project studies/research reports will be undertaken by the consultant to get a holistic desk overview of gaps, lessons learned, good practices. These efforts will enhance content, and other necessary pathways to substantively develop a custom-made and user-centered agri-business curriculum for the selected occupations.

- FGDs and KII from relevant TVET providers, project teams, MoEs and MoLSAF , agri-business companies, youth and other necessary stakeholders to further provide inputs during the curriculum development process.

- Co-design and Curricula Structuring. Develop the design/layout of the curricula/syllabus including scope and sequence, followed by content development including trainer guide and trainee manual. All materials should be experiential with visuals and integrative content.

- Validate the developed curriculum from TVET directorate, IMPACT consortium team, employers including the private sector (agri-business firms) and other relevant stakeholders to finalize the review process and present the adjusted curriculum to SCI for final approval.

- Roll out training for the TOTs from target training institutions to adopt the curriculum. The training will be participatory in nature and combine both theoretical and practical approach to create optimum outcome to the target participants. As agri-business require a lot of hands-on demonstrations, deeper sessions for instructors are key for adoption.

6.KEY DELIVERABLES

- Inception report: detailing the methodology including the main curriculum development methods, research matrix with qualitative research tools, workplan, proposed sources of desk review data including key curriculums to be reviewed and adapted, procedures for data collection (both primary and secondary) and analysis, and a draft but detailed table of contents and layout of each piece (syllabus, trainer guide and trainee manual/handbook). The proposed inception report will be discussed and approved by Save the Children before assignment commences.

- Revised first Draft Final Curriculum. The curriculum should contain syllabus, trainer guide and trainee manual with all resources including teaching aid materials presented through interactive designs (etc visuals)

- Organize a validation workshop to get inputs and views from all relevant stakeholders of the project. The workshop should be designed in a participatory manner to obtain and incorporate suggestions and recommendations from consortium Partners and government line ministries

- A second round of revision may be required before producing the final version of the curriculum. This can ideally be due to further input from government and partners.

- Final designed curriculum (one electronic copy in PDF Format and one in DOC format)

- An electronic copy of all data collection tools of the study with data sets including photos or other graphic captures made during qualitative interviews and TOT sessions for the instructors

Duration of the assignment:

The duration of this assignment overall is 45 days, including preparation of the curriculum and resources as well as training of instructors. Specific schedules will be agreed upon with the selected individual consultant/consultancy firm.

9. QUALIFICATIONS AND EXPERTISE REQUIRED

- Advanced University degree in education, agriculture, learning psychology or Pedagogy, economics, environment or related field

- At least 7 years’ experience in market-oriented curriculum development and training, especially in agri-business or related field

- Experience in client-centered training development and facilitation including the use of participatory tools for information harvesting.

- Demonstrated experience and proven record in employment or workforce development using market systems approach

- demonstrated ability to produce clear, compelling, and succinct analytical report wide variety of stakeholders including the private sector that inform quality curriculum development.

- Excellent communication and documentation skills.

- Strong background and experience in using participatory design process during curriculum development process to align to client needs. ·

- Demonstrable experience in conducting research prior to curriculum development especially in a context similar to Somalia. ·

- demonstrated ability to produce clear, compelling, and succinct but client-centered curriculum that can be adapted and replicated by learning · Excellent communication and documentation skill

10.   APPLICATION PROCEDURE AND REQUIREMENTS:

Interested bidders are expected to provide the following documentation:

- A technical proposal of no more than 20 pages with detailed response to the TOR, with specific focus on understanding the TOR and present a succinct scope of work, methodology for developing the report and outline/layout or key thematic sections of the curriculum. The proposal should also include team composition including their CVs and qualifications

- Initial work plan based on methodology outlined an indication of availability

- Itemized financial proposal including all associated costs (daily fee, travel, logistics etc)

- Samples (minimum 2) of similar work completed.

11.   CODE OF CONDUT:

- Save the Children's work is based on deeply held values and principles of child safeguarding, and it is essential that our commitment to children's rights and humanitarian principles is supported and demonstrated by all members of staff and other people working for and with Save the Children. Save the Children's Code of Conduct sets out the standards which all staff members must adhere to and the consultant is bound to sign and abide to the Save the Children’s Code of Conduct.

- A contract will be signed by the consultant before commencement of the action. The contract will detail terms and conditions of service, aspects on inputs and deliverables. The Consultant will be expected to treat as private and confidential any information disclosed to her/him or with which she/he may come into contact during her/his service.  The Consultant will not therefore disclose the same or any particulars thereof to any third party or publish it in any paper without the prior written consent of Save the Children. Any sensitive information (particularly concerning individual children) should be treated as confidential.

- An agreement with a consultant will be rendered void if Save the Children discovers any corrupt activities have taken place either during the sourcing, preparation and implementation of the consultancy agreement.